**MILESTONES**

* ***Milestones/targets agreed with the promoter based on a review of their objectives and key activities within the proposed work-plan***
* ***A revised time line for actions may need to be re-submitted, include on agreed action sheet***

|  |  |  |
| --- | --- | --- |
|  | **Milestones/Key targets to ensure action plan will be completed within the agreed timeframe**  Recommendations for inclusion in Letter of Offer | **Timeframe for achievement** |
|  | **2018/2019 Milestones Time Frame** | |
| 1 | Literature promoting the Peace IV project | Month 1 & 2 |
| 2 | Web & Social Media promoting Peace IV project | Month 1 & 2 |
| 3 | Community Festival (including Game of Two Halves) at St Peters GAA | Month 1 |
| 4 | Summer Camp 1 | Month 3 & 4 |
| 4 | Procurement Process (as applicable) | Month 1 to 3 |
| 5 | School Assemblies (16 number) & Pre-project surveys  Schools 1 to 4  Schools 5 to 10  Schools 11 to 16 | Month 5 to 6  Month 8  Month 12 |
| 6 | Jacob Stockdale into Partner Schools | Month 5 to 18 |
| 7 | After School Activities (6 blocks x 12 weeks)  Schools 1 to 4  Schools 5 to 10  Schools 11 to 12 | Months 6 to 8  Months 9 to 11  Months 12 to 14 |
| 8 | After School Activities (2 blocks x 4 weeks)  Schools 13 to 16 | Month 13 |
| 9 | Community Festival (including Game of Two Halves) at Eire Og GAA | Month 8 |
| 10 | Ladies Rugby (over 18's) 2 blocks x 8 weeks  Block 1  Block 2 | Month 10 & 11  Month 16 & 17 |
| 11 | Contact Sport Blitz’s (6 number)  Blitz 1  Blitz 2  Blitz 3  Blitz 4  Blitz 5  Blitz 6 | Month 3  Month 4  Month 9  Month 12  Month 15  Month 16 |
| 12 | Field Trips (See Programme) | Month 10 to 17 |
| 13 | Lurgan Rugby Club League or Cup Match | Month 12 |
| 14 | St Peters GAA League or Cup Match | Month 13 |
| 15 | Eire Og GAA League or Cup Match | Month 14 |
| 16 | Ulster Rugby & Armagh GAA joint training | Month 14 |
| 17 | Community Festival 3 (hosted at Pollock Park) | Month 15 |
| 18 | Summer Camp 2 | Month 15 & 16 |
| 19 | Workshops (6 number)  Workshop 1  Workshop 2  Workshop 3  Workshop 4  Workshop 5  Workshop 6 | Month 9  Month 12  Month 14  Month 15  Month 16  Month 17 |
| 20 | Post project Surveys | Month 9  Month 12  Month 15  Month 17  Month 18 |
| 21 | Report writing (every quarter) | Month 4 and each  Quarter thereafter |
| 22 | Final Report | Month 18 |