## Sheet1
Lurgan RFC & CC PEACE IV Programme 2018 - 2019
|  |  | Summer Holidays | [11 empty] | Summer Holidays
Item Description | Month 1 | June | July | August | Sept | Oct | Nov | Dec | Jan | Feb | March | April | May | June | July | August | Sep | Oct | Nov | NOTES
Project Awareness
Literature promoting the Peace IV project | bar: June to Summer Holidays July
Web & Social Media promoting Peace IV project | bar: June to Summer Holidays July
Jacob Stockdale into Partner Schools | bar: Summer Holidays Sept to Summer Holidays June; Summer Holidays Sep to Summer Holidays Nov
Project Administration
Procurement Process (if applicable) | bar: June to Summer Holidays August
School Assemblies (16 number) | bar: Summer Holidays Sept to Summer Holidays Oct; Summer Holidays Dec; Summer Holidays March
Pre-Surveys (16 number schools) | bar: Summer Holidays Sept to Summer Holidays Oct; Summer Holidays Dec; Summer Holidays March
Work Shops (6 number) | bar: Summer Holidays Jan; Summer Holidays April; Summer Holidays June to Summer Holidays Oct
Post Surveys (16 number schools) | bar: Summer Holidays Jan; Summer Holidays April; Summer Holidays July; Summer Holidays Sep to Summer Holidays Nov
Work Shops feedback | bar: Summer Holidays Sept; Summer Holidays Jan; Summer Holidays April; Summer Holidays July; Summer Holidays Sep to Summer Holidays Nov
Reporting Writing | bar: Summer Holidays Jan; Summer Holidays April; Summer Holidays July; Summer Holidays Sep to Summer Holidays Nov
Submit Interim Reports to PEACE IV Management | bar: Summer Holidays Sept; Summer Holidays Dec; Summer Holidays April; Summer Holidays August
Submit Final Reports to PEACE IV Management | bar: Summer Holidays Nov
School Activities
After School Activities (6 blocks x 12 weeks)
Schools 1 & 2 |  | Summer Holidays Jan: 1 & 2
Schools 3 & 4 |  | Summer Holidays Jan: 3 & 4
Schools 5 & 6 |  | Summer Holidays April: 5 & 6
Schools 7 & 8 |  | Summer Holidays April: 7 & 8
Schools 9 & 10 |  | Summer Holidays April: 9 & 10
Schools 11 & 12 |  | Summer Holidays July: 11 & 12
Schools 13 & 14 |  | Summer Holidays July: 13 & 14
Schools 15 & 16 |  | Summer Holidays July: 15 & 16
Community Activities
Community Festivals (3 number) |  | June: 1; Summer Holidays Jan: 2; Summer Holidays August: 3
| Game of Two Halves at St Peters GAA | Summer Holidays Dec: Game of Two Halves at Eire Og GAA; Summer Holidays July: Hosted at Pollock Park
Ladies Rugby
Ladies Rugby (over 18's) 2 blocks x 8 weeks | bar: Summer Holidays Feb to Summer Holidays March; Summer Holidays August to Summer Holidays Oct
Trips
Cross Border Trips (Croke Park & Aviva) | bar: Summer Holidays April; Summer Holidays Sep to Summer Holidays Oct
Somme Centre & Ulster Museum | bar: Summer Holidays March; Summer Holidays June
Cross Border trip Famine Village | bar: Summer Holidays April; Summer Holidays Sep to Summer Holidays Oct
Boyne Heritage Centre | bar: Summer Holidays Feb; Summer Holidays Sep to Summer Holidays Oct
St Peters GAA League or Cup Match | bar: Summer Holidays May
Eire Og GAA League or Cup Match | bar: Summer Holidays June
Pollock Park Activities
Contact Sports Blitz (6 number) | bar: Summer Holidays Jan; Summer Holidays April; Summer Holidays July to Summer Holidays August
Lurgan Rugby Club League or Cup Match | bar: Summer Holidays April
Ulster Rugby & Armagh GAA joint training | bar: Summer Holidays June
Summer Camps (2 number x 2 weeks) | bar: Summer Holidays July to Summer Holidays August